## Sheet1
Task | Owner | Assign Date | To Be Completed | Status | Completed On | Delay if any
Git Setup | Karan | 24/3/2017 | 24/3/2017 | Completed | 26/3/2017 | 2 days
User story elaboration | Karan & Lokesh | 24/3/2017 | 25/3/2017 | Yet to start
Database Designing | Karan & Lokesh | 24/3/2017 | 26/3/2017 | Yet to start
Basic Blog | Karan | 27/3/2017 | 27/3/2017 | Completed | 27/3/2017 | None
Basic Authentication | Karan | 27/3/2017 | 28/3/2017 | Completed | 28/3/2017 | None
Basic Registration | Karan | 27/3/2017 | 28/3/2017 | In Progress
Basic searching | Karan | 27/3/2017 | 28/3/2017
Basic Forum | Karan | 27/3/2017 | 30/3/2017